## Template
California Department of Transportation Transportation Planning Grants Fiscal Year 2018-19 PROJECT TIMELINE
| Project Title | INFRASTRUCTURE FOR PROSPERITY IN THE CENTRAL VALLEY'S INDUSTRIAL TRIANGLE (IPIVIT) PLAN | [14 empty] | Grantee | [6 empty] | FRESNO COUNCIL OF GOVERNMENTS
|  | Fund Source |  |  |  |  | Fiscal Year 2018/19 | [11 empty] | FY 2019/20 | [11 empty] | FY 2020/21
Task Number |  | Responsible Party | Total Cost | Grant Amount | Local Cash Match | Local In-Kind Match | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | Deliverable
1 | PROJECT INITIATION & COORDINATION
1.1 | KICK-OFF MEETING | COG & CITY & COUNTY | 700 | 560 | 0 | 140 | [36 empty] | MEETING NOTES | bar: Fiscal Year 2018/19 S
1.2 | PROJECT TEAM MEETING | COG | 900 | 720 | 0 | 180 | [36 empty] | MEETING NOTES | bar: Fiscal Year 2018/19 O
1.3 | CONSULTANT SELECTION | COG | 1700 | 1360 | 0 | 340 | [36 empty] | RFP DOCUMENTATION & CONSULTANT AGREEMENT | bar: Fiscal Year 2018/19 O to Fiscal Year 2018/19 J
1.4 | CONSULTANT KICK-OFF MEETING with the Project Team | CONSULTANT/COG | 3000 | 2400 | 184 | 416 | [36 empty] | MEETING NOTES | bar: Fiscal Year 2018/19 F
1.5 | COORDINATION MEETINGS | COG | 16000 | 12800 | 0 | 3200 | [36 empty] | MEETING NOTES | bar: Fiscal Year 2018/19 M to FY 2020/21 S
1.6 | REVIEW EXISTING PLANS | CONSULTANT | 10000 | 8000 | 2000 | 0 | [36 empty] | SUMMARY OF FINDINGS | bar: Fiscal Year 2018/19 M to Fiscal Year 2018/19 A
2 | DATA COLLECTION
2.1 | LOCAL & REGIONAL DATA | CONSULTANT | 17500 | 12000 | 5500 | 0 | [36 empty] | SUMMARY OF DATA COLLECTED, DATA FILES | bar: Fiscal Year 2018/19 M to FY 2019/20 J
2.2 | PROJECT AREA DATA | CONSULTANT | 17500 | 12000 | 5500 | 0 | [36 empty] | SUMMARY OF EXISTING CONDITIONS, IMAGES | bar: Fiscal Year 2018/19 M to FY 2019/20 J
2.3 | PROJECT AREA DATA | CONSULTANT | 55000 | 40000 | 14584 | 416 | [36 empty] | PRELIMINARY PLAN LINES, DATA | bar: Fiscal Year 2018/19 M to FY 2019/20 J
2.4 | PROJECT TEAM MEETING | CONSULTANT | 2500 | 2000 | 0 | 500 | bar: FY 2019/20 A
2.5 | CALTRANS REVIEW | CONSULTANT & CALTRANS | 1000 | 800 | 200 | 0 | [36 empty] | CALTRANS WRITTEN COMMENTS | bar: FY 2019/20 A
3 | PUBLIC OUTREACH AND COMMUNITY ENGAGEMENT
3.1 | COMMUNITY ENGAGEMENT PLAN | CONSULTANT | 20000 | 16000 | 4000 | 0 | [36 empty] | PLAN DOCUMENT | bar: FY 2019/20 J to FY 2019/20 A
3.2 | PROJECT TEAM MEETING | CONSULTANT | 2500 | 2000 | 0 | 500 | bar: FY 2019/20 S
3.3 | CALTRANS REVIEW | CONSULTANT | 1000 | 800 | 200 | 0 | [36 empty] | WRITTEN APPROVAL | bar: FY 2019/20 S
3.4 | COMMUNITY MEETING PROMOTION | CONSULTANT | 7500 | 6000 | 1084 | 416 | [36 empty] | FLYERS & PROMOTIONAL MATERIALS | bar: FY 2019/20 S to FY 2019/20 N
3.5 | COMMUNITY MEETINGS (4) & PUBLIC COMMENT | CONSULTANT | 30000 | 24000 | 1840 | 4160 | [36 empty] | MEETING SUMMARY, MEETING MATERIALS: IMAGES, HANDOUTS, SIGN-IN SHEETS | bar: FY 2019/20 N to FY 2019/20 D
4 | DRAFT INFRASTRUCTURE FOR PROSPERITY IN THE CENTRAL VALLEY'S INDUSTRIAL TRIANGLE (IPIVIT) PLAN
4.1 | PRODUCE DRAFT IPIVIT PLAN WITH IMPLEMENTATION PLAN AND FUNDING MATRIX | CONSULTANT | 97000 | 72800 | 24200 | 0 | [36 empty] | DRAFT PLAN WITH IMPLEMENTATION PLAN AND FUNDING MATRIX | bar: FY 2019/20 J to FY 2019/20 M
5 | PLAN FINALIZATION
5.1 | HOLD A REVIEW MEETING | CONSULTANT | 2500 | 2000 | 0 | 500 | [36 empty] | MEETING NOTES | bar: FY 2019/20 J
5.2 | FINALIZE IPIVIT PLAN | CONSULTANT | 15000 | 12000 | 3000 | 0 | [36 empty] | FINAL DRAFT PLAN | bar: FY 2020/21 J
5.3 | FINAL DRAFT TO CALTRANS | CONSULTANT | 1000 | 800 | 200 | 0 | [36 empty] | CALTRANS WRITTEN COMMENTS & APPROVAL | bar: FY 2020/21 A
5.4 | FINAL PLAN | CONSULTANT | 14000 | 8000 | 6000 | 0 | [36 empty] | PLAN DOCUMENT | bar: FY 2020/21 A
6 | FRESNO COUNCIL OF GOVERNMENTS BOARD ADOPTION
6.1 | PRESENT PLAN TO FRESNO COG BOARD | FRESNO COG & CONSULTANT | 1000 | 800 | 200 | 0 | [36 empty] | BOARD MEETING MINUTES | bar: FY 2020/21 S
7 | FISCAL MANAGEMENT AND REPORTING
7.1 | PROJECT MANAGEMENT | FRESNO COG | 500 | 400 | 100 | 0 | [36 empty] | ACHIEVEMENT OF PROJECT MILESTONES | bar: Fiscal Year 2018/19 O to FY 2020/21 S
7.2 | INVOICING FOR REIMBURSEMENT | FRESNO COG | 500 | 400 | 100 | 0 | [36 empty] | INVOICE PACKAGES | bar: Fiscal Year 2018/19 J; Fiscal Year 2018/19 M; FY 2019/20 S; FY 2019/20 J; FY 2019/20 M; FY 2020/21 S
7.3 | REPORTING | COG & CONSULTANT | 500 | 400 | 100 | 0 | [36 empty] | REPORTS | bar: Fiscal Year 2018/19 N; Fiscal Year 2018/19 F; Fiscal Year 2018/19 M; FY 2019/20 A; FY 2019/20 N; FY 2019/20 F; FY 2019/20 M; FY 2020/21 A
| TOTALS |  | 318800 | 239040 | 68992 | 10768
Reimbursement of indirect costs is allowable upon approval of an Indirect Cost Allocation Plan for each year of project activities. Provide rate if indirect costs are included in the project budget. Approved Indirect Cost Rate: ______%
Note: Each task must contain a grant amount and a local cash match amount. Local cash match must be proportionally distributed by the same percentage throughout each task. Local in-kind match needs to be indicated where in-kind services will be used. Please review the grant program section that you are applying to for details on local match requirements. The project timeline must be consistant with the scope of work.