## Cycle 2 #1 & #2
Project Title: |  | Analysis & Operational Plan for Rural Transit Services
Task # | Task Title | Responsible Party | Budget | FY 2018/2019 | [11 empty] | FY 2019/2020 | [11 empty] | FY 2020/2021 | [11 empty] | Deliverable
|  |  | Total Cost | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J
1 | Project Initiation
1.1 | RFP for Consultant Services & Award of Consulting Contract | FCRTA/FCOG | 0 | [36 empty] | RFP Document, Copy Executed Consultant Contract
2 | Public Meetings
2.1 | Project Introduction Meeting | Consultant | 4000 | [36 empty] | Power Point Presentation, Meeting Summary, Photos, List of attendees
2.2 | Community Workshop #1 | Consultant | 4500 | [36 empty] | Power Point Presentation, Workshop Summary, Photos, List of attendees
2.3 | Community Workshop #2 | Consultant | 4500 | [36 empty] | Power Point Presentation, Workshop Summary, Photos, List of attendees
2.4 | Community Workshop #3 | Consultant | 4500 | [36 empty] | Power Point Presentation, Workshop Summary, Photos, List of attendees
3 | Consultant Work
3.1 | Project Kick-Off Meeting/Identify Project Issues | Consultant | 16000 | [36 empty] | Meeting Notes, Summary of Project Issues
3.2 | Develop Initial Findings Re: Project Issues | Consultant | 15000 | [36 empty] | Written Findings & Early Draft Report
3.3 | Determine Operational Plan | Consultant | 21000 | [36 empty] | Draft Operational Plan & Revised Draft Report
3.4 | Determine All Project Costs | Consultant | 15000 | [36 empty] | Written Findings & Revised Draft Report
3.5 | Determine Funding Options | Consultant | 15000 | [36 empty] | Written Findings & Revised Draft Report
3.6 | Complete Draft Program Study Report | Consultant | 30000 | [36 empty] | Draft Report
3.7 | FCRTA Review/Comment on Draft Report | Consultant | 8756 | [36 empty] | FCRTA Revisions for Draft Report & Revised Report
3.8 | Complete Final Program Study Report | Consultant | 18000 | [36 empty] | Final Report
3.9 | FCRTA Board Adoption | Consultant | 300 | [36 empty] | Board Resolution & Distribution of Final Report
4 | Fiscal Management
4.1 | Invoicing | Consultant | 1000 | [36 empty] | Invoice Documents
4.2 | Quarterly Reports | Consultant | 1500 | [36 empty] | Quarterly Reports
5 | Miscelleneous
5.1 | Workshop Support | Consultant | 1500 | [36 empty] | Administrative tasks for Workshops
| TOTALS |  | 160556